## Project plan
| SK251 PA_SOP 32/16 | [6 empty] | 2015 | [51 empty] | 2016
[7 empty] | Month | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
[7 empty] | Ideal PEP 48 | -19 |  |  |  | -18 |  |  |  |  | -17 |  |  |  | -16 |  |  |  |  | -15 |  |  |  | -14 |  |  |  | -13 |  |  |  |  | -12 |  |  |  | -11 |  |  |  | -10 |  |  |  |  | -9 |  |  |  | -8 |  |  |  | -7 |  |  |  | -6 |  |  |  |  | -5 |  |  |  | -4 |  |  |  |  | -3 |  |  |  | -2 |  |  |  | -1 |  |  |  |  | 0 |  |  |  | 1 |  |  |  | 2 |  |  |  |  | 3
[7 empty] | CW | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Sr No |  | Project Plan
1
| Sr No | Task | Date of Assign | Target Date | Actual Date | Progress | Notes
| 1 | DLV of PMP | 15.06.15 |  | 14.07.15 | 100
| 2 | Design Data confirmation | 15.06.15 |  | 07.07.15 | 100 | Data shared with supplier
| 3 | MP- Umbrella evaluation | 22.06.15 | 25.06.15 | 24.06.15 | 100
| 4 | Criticle part time line | 22.06.15 | 24.06.15 | 24.06.15 | 100
| 5 | DLV Launch cost | 22.06.15 |  |  | 100 | Received
| 6 | MB/C build plan | 22.06.15 |  |  | 100
| 7 | Car protection cover | 23.06.15 | 26.06.15 | 25.06.15 | 100
| 8 | Project review doc | 30.06.15 | 03.07.15 | 01.06.15 | 100
| 9 | Car planning appicability | 03.07.15 | 07.07.15 |  | 80 | New line structure
| 10 | Wiper desgin change | 03.07.15 |  |  | 50 | Decision to be made for SK251 PA
| 11 | Stufen Plan | 07.07.15 |  |  | 0 | Awaited from Ramp up
| 12 | Fugen Plan: Clarity about section F41_1 | 08.07.15 |  |  | 70 | Proposal send to MB
| 13 | TPB evaluation for side Air bag | 09.07.15 |  |  | 100 | Feedback awaited from SQA, Lab
| 15 | Modele Year PPT | 10.07.15 |  |  | 100
| 16 | Lab testing plan | 12.07.15 | 21.07.15 |  | 30 | Under preparation
| 17 | KVS excess | 13.07.15 |  |  | 0
| 18 | Validation of Radio, Horn bracket, Instrument cluster | 14.07.15 |  |  | 100 | ASL
| 19 | PMP review with measurement room | 14.07.15 |  |  | 30 | PMP & FMK received, data under verification
| 20 | Car planning change for car order FBW & SOSi | 20.07.15 |  |  | 100 | Ask for both testing
| 21 | Blak body requirement for PVS & 0S |  |  |  | 20 | Under disscusion
| 22 | Car planning AKN understanding |  |  |  | 0 | New 3 line structure
| 23 | Car Content |  |  |  | 0 | New 3 line structure
| 24 | Quality Target |  |  |  | 0
| 25 | Management drive plan |  |  |  | 30 | Proposal recevied from MB
OS
SOP
BF
LF
VFF
PVS

## Activities
On going Activity |  |  |  | Top issues
Sr. No | Activity | Notes | Status | Sr. No | Activity | Notes | Status
1 | Aeko Overview |  | 100 | 1 | Window lifter motor Gen 3 (SOP 03/16) | Part avail isusse | 100
2 | Visit Report |  | 100 | 2 | Glossy logo on steering wheel BMG fail (SOP 03/16) | SOP 32/16 for india & 22/16 for Europ | 100
3 | Group ID creation |  | 100 | 3 | MAT 1 Alloy wheel localization | SOP needs to be check | 0
4 | Protocol Q project meeting |  | 100 | 4 | 16" Alloy wheel | Nomination | 0
5 | Claim settlement |  | 100 | 5 | Quality Target for Project SK251 PA |  | 0
6 | Agenda for Q project meeting |  | 100 | 6 | Management drive plan |  | 0
7 | KVS acess | Need to check with Amit Sir | 0 | 7 | SK251 PA : Section F41_1 | Proposal send to MB | 0
8 | Common folder space increase |  | 100
9 | Vento NF ideas Quality review |  | 100
10 | Visit cost invoices | Awaited from Joyniel | 0
11 | Leave plan for the year |  | 100
12 | MAT 1 alloy wheel SOP confirmation |  | 0
13 | 16" Alloy wheel Supplier |  | 0
14 | Meeting with controling for Lab cost for car testing | Mr. Sheelvat will do meeting | 100
15 | Q project meeting Agenda CW29 |  | 100
16 | One pager for Mr. Stephan |  | 100
17 | Fugen plan F41_1 section comparision |  | 0
18 | Protocol Q project meeting |  | 100
19 | Vento NF ideas Quality review: Verification | Circulated to the team | 0
20 | Blak body requirement for PVS & 0S |  | 0
21 | Car planning AKN understanding |  | 0
22 | Car Content |  | 0
23 | Agenda for Q project meeting |  | 100
24 | H4 & H7 Head lamp data for SK251 PA COP from Fabia Europe |  | 0