## SK251 PA Project Plan Plan
SK251 PA Project Time Plan
Description |  |  | 2015 | [52 empty] | 2016
|  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | April |  |  |  | May
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Current Timeline | [107 empty] | Remarks
Preparation of Pilot Hall
VPH SK251 PA
Pre-meeting
TOP MNG Meeting
Quality Documents for Pilot Hall
Car Planning
ASL Status
Management Drive Plan
Measurement Room Status
CP5 EMPB Status
CP7 EMPB Status
2DP Status
Launch Plan
Konzern Target
Reipergradspiegal
Change Request
MP |  |  | Jan 2: 1; Feb 6: 3; Feb 9: 1; Mar 13: 1; Apr 15: 1; May 19: 1; May 20: 1; May 21: 2; Jun 24: 1; Aug 32: 1; Nov 49: 1; Feb 6: 1; April 16: 1; May 22: 1; May 25: 1
Aeko |  |  | Jan 3: 2; Jan 4: 1; Jan 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 12: 1; Mar 13: 3; Apr 18: 2; May 21: 1; Jun 23: 1; Jun 24: 1; Jun 26: 2; Jul 28: 1; Jul 29: 2; Aug 35: 3; Aug 36: 1; Oct 41: 3; Oct 43: 1; Oct 44: 5; Nov 45: 2; Nov 47: 1; Dec 50: 1; Feb 6: 1; Feb 8: 2; Mar 10: 2; Mar 11: 2; Mar 13: 1; April 16: 1; April 17: 1; May 18: 1; May 21: 1; May 22: 1; May 23: 2; May 24: 1; May 25: 1; May 26: 1; May 27: 1
AWE |  |  | Jul 31: 1; Aug 34: 1; Feb 5: 1; Mar 9: 1; Mar 12: 1; April 16: 1; April 17: 5; May 22: 1; May 24: 1
Part Readiness
Fender(2) | TP05611E | SOLL 1 | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | TO IN Laser cut | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | T3 Tool Release | 1 | 1 | N3* Sub | 1 | 1 | 1 | 2 N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release |  | CW 35: Op - 20 Punch Cracked observed, no impact on timeline. New punch manufacturing is in process. New Punch Detailed Timeline awaited from SRM/Purchase CW40: Draw die try-ot started. Further dies under 3D machining. 1st 10sets of laser cut parts submission date not yet confirmed 42/1 or 42/5. All activities are planned conisdering aval. 42/1. CW41: 10 sets of laser cut Parts are dispatch. CW42: Laser cut parts are received CW42/2,3 @ Measurement room,4 Measurement starts. CW43: Measurement is done. CW46: Tooled up parts are received.Parts are not good condition. CW 47: Parts measurement is done, also replaced on AMB. Good sampled parts by Quality will be retrofitted on SOFA car & other car if required. CW49:Timeline must be revise for part availbility & schedule plan in Gestamp. Parts for PVS will be N6. Task from PH, quality must check to squeeze timeline for N1 optimization. CW 50: Fender must be corrected @ headlamp area & contact surface side panle. CW 53: Parts are submiited for car build. LH: AK13, BK04,Z0. QK:4.8 RH: AK11,BK04,Z0. QK:4.9 CW03: Teiletisch is done in CW02. Target for the tool shipment is given CW10. Detail timeplan & step of action is still awaited. CW05: PVS 04S parts are received. CW06: Next Teiletisch planned in CW09. CW08: - OP60/70 spotting work almost finished, OP40 milling started.
|  | SOLL 2 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: TO IN Laser cut; Oct 43: 1; Oct 44: 1; Nov 45: T0; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: PVS Production; Dec 52: 1; Dec 53: PVS Sub; Jan 2: N3* Production; Jan 3: N3* Sub; Jan 4: 1; Feb 5: 1; Feb 6: N3* sub & Tool transfer start; May 25: N3 Sub
|  | Soll 3 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: TO IN Laser cut; Oct 43: 1; Oct 44: 1; Nov 45: T0; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: Tryout parts received; Jan 1: 1; Jan 2: 1; Jan 3: 04S; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 05S; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: N3* Release & Tool transfer start; May 46: N3 Sub; May 50: N3 Release
|  | IST | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: TO IN Laser cut; Oct 43: 1; Oct 44: 1; Nov 45: T0; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: Tryout parts received; Jan 1: 1; Jan 2: 1; Jan 3: 04S; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 17: 1; May 18: Project Doc\CW17_SK251 PACritical part status.pptx; May 22: 1; May 23: 1; May 24: 1
Bonnet outer(1) | TP05611E | SOLL 1 | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | TO IN | 1 | T2 | T2 | 1 | T3 Tool Release | 1 | 1 | N3* Sub | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release |  | CW 35: Series Location N3 Submision dates under Discusion with Gestamp, will be confirmed till end of CW35/15 - SRM/Purchase N3* Sub in CW46 official protocol is awaited Teiletisch is planned in CW37 in Yifeng, China. CW40: Checking for Spotting OK. Tornado line stoned & polished, it may affect finishing of tornado line, awaited for part. CW 41: N3 parts submission change to CW 09/16. ZSB measurement is done in measurement room CW41/4. More clamps required by getstap for bonnet outer measurement. CW43: Additional clamp declined by Mr. Kola & SK press planning. provision of additional RPS is in discussion. CW45: Teiletish was planned. CW 46: Bonnet is big than CAD data in Y problem is undder analysis. Angle angle at windshiled area is 90 deg, where as required angle is 115 deg. CW 47: As per problem sheet N3* submission was in CW47, which was not happened. CW48: Tryout Parts are received for hemming optimization. CW49:Timeline must be revise for part availbility & schedule plan in Gestamp. Task from PH, quality must check to squeeze timeline for N1 optimization. CW50: 10 sets of try out parts will be send for detail evaluation based on results furthur plan for PVS parts to be made. CW 51: 10 sets are submitted with correction in width, CMM reports are submitted, Hemming feedback is awaited. CW 53: Parts are submiited for car build. CW03: Teiletisch is done in CW02. Target for the tool shipment is given CW10. Detail timeplan & step of action is still awaited. CW05: PVS Part are received. Y correction supplier measurement reports are submitted. AK: 11,BK:01,Z:00. QK:3.7. CW07: Bonnet Outer 04S QK2.6. Hemming optimization is going. Hemming optimization feedback is given to Yifeng. - Parts are correct in Y-direction. - Correction to be done in X- direction @ emblem area. - Improved parts are expected in CW9. - AMB feed back to be given for the same.
|  | SOLL 2 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: PVS Production; Dec 50: 1; Dec 51: PVS Sub; Dec 52: N3* Production; Dec 53: N3* Sub; Jan 1: 1; Jan 2: 1; Jan 3: N3* Release & Tool transfer start; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; May 48: N1 Sub
|  | SOLL 3 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: Tryout parts received; Nov 49: N3* Production; Dec 50: 1; Dec 51: Tryout parts received; Dec 52: 1; Dec 53: Tryout parts received 03S; Jan 1: Tryout parts received 03S; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1st part after tool modification; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: N3* Release & Tool transfer start; May 37: N3 Sub; May 41: N3 Release; May 51: N1 Sub
|  | IST | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: Tryout parts received; Nov 49: N3* Production; Dec 50: 1; Dec 51: Tryout parts received; Dec 52: 1; Dec 53: Tryout parts received 03S; Jan 1: Tryout parts received 03S; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: N3* Release overall N6 & Tool transfer start; May 37: N3 Sub
Bonnet Inner(1) | TP05611E | SOLL 1 | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 TML | 1 | TO IN | 1 | T2 | T1 | 1 | 1 | T3 Tool Release | 1 | N3* Sub | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release | [8 empty] | CW 35: Series Location N3 Submision dates under Discusion with Gestamp, will be confirmed till end of CW35/15 - SRM/Purchase N3* Sub in CW46 official protocol is awaited Teiletisch is planned in CW37 in Yifeng, China. CW40: Checking for Spotting OK. CW 41: CW 41: N3 parts submission change to CW 09/16. ZSB measurement is done in measurement room CW41/4. CW45: Teiletish was planned. CW49:Timeline must be revise for part availbility & schedule plan in Gestamp. Task from PH, quality must check to squeeze timeline for N1 optimization. CW50: 5 sets of try out parts will be send for detail evaluation based on results furthur plan for PVS parts to be made. CW 51: 10 sets are submitted with correction in width, CMM reports are submitted, Hemming feedback is awaited. CW 53: Parts are submiited for car build. AK: 03 BK:05,Z:00. QK:3. CW02: Toolshipment agrrement is given. CW03 shipment will start. CW05: PVS parts are submitted. CW07: Beon is awaited.
|  | SOLL 2 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: T0 TML; Sep 38: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: N3* Production; Dec 50: N3* Sub; Dec 51: 1; Dec 52: 1; Dec 53: N3* Release & Tool transfer start; May 41: N1 Sub; May 44: N1 Release
|  | SOLL 3 | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: T0 TML; Sep 38: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: Tryout parts received; Nov 49: N3* Production; Dec 50: 1; Dec 51: Tryout parts received; Dec 52: 1; Dec 53: Tryout parts received; Jan 1: 1; Jan 2: 1; Jan 4: N3* Release & Tool transfer start; May 19: N3 Sub; May 21: N3 Sub; May 23: N3 Release; May 38: N1 Sub; May 42: N1 Release
|  | IST | Mar 11: BF; Mar 12: 1; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: T0 TML; Sep 38: 1; Sep 39: TO IN; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: Tryout parts received; Nov 49: N3* Production; Dec 50: 1; Dec 51: Tryout parts received; Dec 52: 1; Dec 53: Tryout parts received; Jan 1: 1; Jan 2: 1; Jan 4: N3* Release & Tool transfer start; May 23: N3 Sub; May 27: N6 Rele; May 37: N3 Sub
Lock Reinforcement |  | SOLL | [12 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | N1 Sub | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [20 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: Parts are received as per plan. Measurement reports from supplier will be refer to give feedback for next gener level. CW48: N3 submission not happen as per plan. CW49:Beon was rejected due to wrong generation level mentioned. CW 50: Beon & Parts submitted for evaluation. CW53: NOTE 6: 1 3 3
|  | IST | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: T0; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: N3 Sub; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: N6 Release; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: N1 Sub; Mar 11: 1; Mar 12: 1; Mar 13: N1 Release; April 14: 1; April 15: 1; April 16: 1
Hinge Reinforcement (2) |  | SOLL | [12 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | N1 Sub | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [20 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: Parts are received as per plan. Measurement reports from supplier will be refer to give feedback for next gener level. CW48: N3 submission not happen as per plan. CW49: Beon was rejected due to wrong generation level mentioned. CW 50: Beon & Parts submitted for evaluation. CW53: NOTE 6: 1 3 3
|  | IST | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: T0; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: N3 Sub; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: N6 Release; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: N1 Sub; Mar 11: 1; Mar 12: 1; Mar 13: N1 Release; April 14: 1; April 15: 1; April 16: 1
Fender Bracket (4) |  | SOLL | [12 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | N1 Sub | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [20 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: Parts are received as per plan. Measurement reports from supplier will be refer to give feedback for next gener level. CW 50: Beon & Parts submitted for evaluation. CW51: Part number engraving not possible on part due to profile. Further feasibility under check by supplier. Reply expected by CW51.05. CW53: NOTE 6:2 Brackets 6 3 6. CW04: Re-submission will be in CW05 CW05: Parts are re-submitted. CW07: Note 6: 3 3 1. CW13: Fender Bracket 5J5805161/162 N1 rest of two brackets are under evaluation. CW14:All brackets are Note1
|  | IST | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: T0; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: N3 Sub; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: N6 Release; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: N1 Sub; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: N1 Release; April 16: 1
Front End Carrier |  | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | part for AMB | 1 | 1 | 1 | 1 | 1 | 1 | parts for VFF | Grain Goahead | 1 | 1 | 1 | Graining Completion | 1 | 1 | 1 | 1 | 1 | Grained parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35 :1st parts under custom clearance expected submision CW35 end. CW 36 : Part received at VW plant CW 37 : GOM measurement was done in CW37 no critical point observed. CW 41 : T1 part is submitted. This part will be fitted on miesterbock. Part is of imported material. CW42: Aeko was created to use local raw material for PVS cars. CW43: Aeko is approved of Raw material. CW 44: Graining go ahed is given. CW51: 5 sets of improved parts as per feedback from VFF are dispatch, part aval dates awaited. CW53:Tooling observation shared to SRM, CW01:Action plan is awaited from SRM.based on which Clearance for shipment will be given. CW02: Tool buy off is done. Grained parts submitted for PVS. CW03: Tools are under shipment. CW06: Tool shipment is done. CW07: Problem observed in PVS build for adjusting Hood latch for maintaining Bonnet radiator grill gap. CW12: Part is not submitted for BMG @ MB CW13: Sample is submitted for N3 evaluation.
|  | IST | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | part for AMB | 1 | 1 | 1 | T1 | 1 | parts for VFF | Grain Goahead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Tool Buy off & Grained parts for PVS | [5 empty] | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | BMG release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Front Bumper (5) |  | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | Part for AMB | 1 | 1 | 1 | 1 | Parts for VFF | Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Grain Completion / Parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | BMG Sub. | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35 :2 weeks delay in 1st part Submision No impact on the project timeline at the moment. CW 39: Parts are submitted. Cubing is awited. CW 40: Feedback is given for T1 parts on the basis of some visual inspection of T0. For T2 level correction cubing report will be available. CW 41 :Cubing trial was done CW41/5. CW 42 : Cubing trial was done for T0 sample,B:03,C1:05. CW 44: Graining go ahed is given. CW50: T2 level bumpers are submitted. CW51: Cubing was done 4 C1 defects are observed. CW52: Tool transfer trail done No major observation found. CW53: Clearance for tool shipment is given. CW01: Tool review Documentation is with Q head. for review. CW02: Tool buy off is done. Grained parts submitted for PVS. CW03: Tools are under shipment. CW05: Tool reached to india. CW06: AMB & Cubing defects are observed & further actions are define. CW07: Part submission from series location in CW08. CW08: Parts are submited for Cubing from serial location. CW12_5: Beon submitted. CW13: IMDS issue, evaluation started.
|  | IST | [11 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | 1 | part for AMB | 1 | Parts for VFF & Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | T2 Parts are submitted | 1 | 1 | 1 | 1 | Tool Buy off & Grained parts for PVS |  |  |  |  | 1 | 1 | 1 | 1 | 1 | N3 Sub | N3 Sub/ BMG Sub @ MB | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | BMG release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Rear Bumper(10) |  | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | Part for AMB | 1 | 1 | 1 | 1 | Parts for VFF | Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Grain Completion / Parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | BMG Sub. | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35 :2 weeks delay in 1st part Submision No impact on the project timeline. CW 39: Parts are submitted. Cubing is awited. CW 40: Feedback is given for T1 parts on the basis of some visual inspection T0. For T2 level correction cubing report will be available. CW 41 : Cubing trial was done CW41/3. CW42 : Cubing dryrun was done CW42.B:03,C:02,C1:01. CW 44: Graining go ahed is given. CW50: T2 level bumpers are submitted. CW51: Cubing was done 4 C1 defects are observed. CW52: Tool transfer trail done . CW53: Clearance for tool shipment is given. CW01: Tool review Documentation is with Q head. for review. CW02: Tool buy off is done. Grained parts submitted for PVS. CW03: Tools are under shipment. CW05: Tool reached to india. CW06: AMB & Cubing defects are observed & further actions are define. CW07: Part submission from series location in CW08. CW08: Parts are submited for Cubing from serial location. CW12_5: Beon submitted. CW13: IMDS issue, evaluation started.
|  | IST | [11 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | 1 | part for AMB | 1 | Parts for VFF & Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | T2 Parts are submitted | 1 | 1 | 1 | 1 | Tool Buy off & Grained parts for PVS |  |  |  |  | 1 | 1 | 1 | 1 | 1 | N3 Sub | N3 Sub/ BMG Sub @ MB | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | BMG release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tail lamp (2) |  | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 T1 | Pre-BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | BMG Sub. | 1 | 1 | 1 | N3 / BMG Release | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: 1st Part sub in CW44. CW50: Delay in photometric test by supplier, hcih results in delay for Pre BMG submission & furthur for tool transfer. CW41 :In CW40 T0 trail was done for lens. CW01: NOTE 6: 6 6 6 CW02: Tools are ready for dispatch, shipment is awaited for Pre-BMG reports. CW04: Tooling go ahead is given. Pre-BMG reports are OK. CW11: N3 & BMG sub in CW14. CW14:N3 Beon submitted, physical part sub awaited.
|  | IST | [15 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | Pre-BMG Sub. | 1 | 1 | 1 | N6 Release | 1 | 1 | [7 empty] | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N6 Release for BMG | 1 | N1 Sub | 1 | 1 | 1 | 1 | N1 Re-Sub | BMG release | 1 | 1 | 1 | N1 Release
Foam part (1) |  | SOLL | Mar 12: BF; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: T0; Jul 30: 1; Jul 31: T0; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: N3 Sub; Jan 4: 1; Feb 5: 1; Feb 6: N3 Release; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: N1 Sub; Mar 12: 1; Mar 13: 1; April 14: N1 Release | CW 35: All activities on track CW 36: Part under Q evaluation CW 37: Part under Q evaluation CW38: Multicavity go ahead is given. CW01: Toolshipment is done. CW02:Tool shipment is done. CW05: Parts are submitted from series location.
|  | IST | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | N1 Release
Bumper Bar front (1) |  | SOLL | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35: All activities on track For Paralellism spec ICS actions to be followed CW 36: All activities on track CW 37: All activities on track CW40: All activities on track CW04: M:6 L:-- F:3 CW07: Improved part is submitted with mounting hole correction.
|  | IST | [10 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1
Decklid Chrom strip (1) |  | SOLL | [20 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: All activities on track CW07: Improved part is submited for fitment trail, & new parts are submitted for lab testing.
|  | IST | May 21: BF; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: T0; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: N3 Sub; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: N3 Release; Mar 11: 1; Mar 12: N1 Sub; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: 1; May 21: N1 Release
Hood Latch (1) |  | SOLL | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 MLF Release | 1 | BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release w/o BMG | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40 : Part submission need to check as per time line CW 50: Part is submitted for evaluation, corrosion tests are not part of PAB as part is COP from VW. BTV & Lab must check requirement. CW04: M:-- L:-- F:3 CW09: N1 submission 15/16. CW11: 3,-,3-6 N1 submission dates to confirmed. CW13: 3 1 3:6
|  | IST | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N6 Release | 1 | 1 | N6 Release for BMG | 1 | N1 Release w/o BMG | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | 1 | 1 | 1 | N1 Release
Air duct (2) |  | SOLL | Apr 15: BF; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: Parts for VFF; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: N3 Sub; Nov 49: N3 Release; Jan 3: N1 Sub; Feb 5: N1 Release; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: 1; May 28: 1; May 29: 1; May 30: 1; May 31: 1; May 32: 1 | CW 35: All activities on track CW 36: Part under Q evaluation CW 37: Part under Q evaluation CW 38: Multi cavity go ahed is given.Delay in Tool trasportation CW40:Tool will be transfer in not yet started.Need to check for serial parts submission. CW42: Multi cavity tool CMM reports are submitted . Go ahead is given for Tool shipment CW42/5. CW45: Tool is lifted from tool maker location. CW01: Toolshipment is done. CW04: Part is submitted for evaluation from series location. CW12 : N1 submission CW14/16.
|  | IST | Apr 15: BF; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: T0 Single cavity tooled part; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: Parts for VFF; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: N3 Sub; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: N3 Release; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: N1 Release w/o BMG; April 17: 1; May 18: 1
Bowden cable (1) |  | SOLL | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | ; | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | [20 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW 37: All activities on track CW40: All activities on track CW04: Closed as a 1 3 3: 6, without BMG
|  | IST | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | BMG Sub. | 1 | 1 | N6 release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Horn (2) |  | SOLL | [16 empty] | B Release | [8 empty] | BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | CW 35: All activities on track CW07: N1 Release BMG release done
|  | IST | Feb 9: B Release; Jun 26: BMG Sub.; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: N1 Sub; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: N1 Release BMG release done
Radio (1) |  | SOLL | Jul 30: BF; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: Parts for VFF; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: N3 Sub; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: N3 Release; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: N1 & BMG Sub.; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: BMG release; May 28: N1 Release; May 29: 1; May 30: 1; May 31: 1; May 32: 1; May 33: 1; May 34: 1; May 35: 1; May 36: 1; May 37: 1; May 38: 1 | Late Product marketing decision for MIBG Standard plus Radio Delayed timeline from Santana China base Project CW 35 : All activities on track CW 36 : BF is delayed to CW37. Critical for VFF. CW 02: Part is submitted for N3. Beon ie resend. CW 07: Part is taken for evaluation.
|  | IST | Sep 37: BF; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: Parts for VFF; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: N3 Sub; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: N6; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: N3 Sub & re-send; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: 1; May 21: N3 Sub; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: N6 release; May 28: 1; May 29: 1; May 30: 1; May 31: 1; May 32: 1; May 33: 1; May 34: 1; May 35: 1; May 36: 1; May 37: 1; May 38: 1; May 39: 1
Seat Covers (6) |  | SOLL | Sep 39: Fakom Presentation; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: B Release; Dec 52: 1; Dec 53: 1; Jan 1: N3 Sub; Jan 2: 1; Jan 3: 1; Jan 4: BMG Sub N3 Release; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: 1; May 28: 1; May 29: N1 Sub; May 30: 1; May 31: N1 Release/BMG release; May 32: 1; May 33: 1; May 34: 1; May 35: 1; May 36: 1; May 37: 1; May 38: 1 | CW04: Part is submitted for N3. Fabric release report is missing. CW07: No clarity for release report.
|  | IST | Sep 39: Fakom Presentation; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: B Release; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: BMG Sub N3Sub; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: N3 release: Overall N6; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: 1; May 28: 1
Carrier Part (2) |  | SOLL | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | BMG Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [21 empty] | CW 35: All activities on track CW 36: All activities on track CW 37: All activities on track CW40: All activities on track CW04: M:3 L:-- F:-- CW05: M:3 L:-- F:3of Tool maker location CW14: 3 1 3: 6, because
|  | IST | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Release | 1 | N1 Sub | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15" Alloy Wheel MAT 1 |  | IST | Aug 35: BF; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: T0 CKD; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: BMG Sub.; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: BMG release; Feb 8: N3 Sub; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: N3 Release; April 14: 1; April 15: 1; April 16: Risk Release; April 17: N1 Sub; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: Q Release; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: N1 Release; May 28: 1; May 29: 2DP; May 30: 1; May 31: 1 | Quality will give release after complition of target meilage of 50,000km CW 35: All activities on track, B release was done in CW35 at supplier end. CW 36: BF in System is pending. Further activities on track. CW 37:System release is pending. Further activities on track. CW 40 : BF is done in system. CW 41 : Meeting was scheduled to review time line. BMG sub & release dates need to be confirm. CW 42 :BMG release may gets delay.It wil affect part aval. for PVS so Q release will be given after 50,000km ( CW27). CW43: No delay in BMG dates. CW49: BMG is delayed by 2 weeks, from CW07 to CW09. CW07: BMG testing is done. System release is in CW09. CW11: Parts are Retrofitted in to car with 11839
|  | SOLL | Sep 40: BF; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: T0 CKD; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: BMG Sub.; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: BMG release; Mar 10: 1; Mar 11: N3 Sub; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: N3 Release; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: 1; May 28: 1
Door Trim |  | IST | Jun 25: BF; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: T0; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: N3* Sub; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 5: N3 Sub; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: N1 Sub; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: N1 Release | CW03: N3 release 3 3 1
|  | SOLL | Jun 25: BF; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: T0; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: N3* Sub; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: N3 release; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; May 18: 1; May 19: 1; May 20: N1 Sub; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: N1 Release
Head lamp leveling switch |  | IST | Nov 48: BF; Nov 49: 1; Dec 50: Proto Parts; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: T0 & Grain release; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: N3 Sub; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: N3 Release; April 14: 1; April 15: 1; April 16: N1 Sub; April 17: BMG release; May 18: 1; May 19: N1 Release | Not yet clarity about the part local or CKD. CW48: Time line sing off is done, delay for part aval for PVS. CW03: Resistance value defined. CW04: Issues with illumination. CW09: H4 leveling switch T1 Part is submitted for ASL, H7 part is awaited with resistance value correction.
|  | SOLL | Nov 48: BF; Nov 49: 1; Dec 50: Proto Parts; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: T0 & Grain release; Jan 4: 1; Feb 5: 1; Feb 6: 1; Feb 7: 1; Feb 8: 1; Mar 9: T1 Part is submitted for ASL; Mar 10: 1; Mar 11: 1; Mar 12: N3 Sub; Mar 13: 1; April 14: 1; April 15: 1; April 16: 1; April 17: N6 Release; May 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; May 23: 1; May 24: 1; May 25: 1; May 26: 1; May 27: 1; May 28: 1; May 29: 1; May 30: 1; May 31: 1; May 32: 1; May 33: 1; May 34: 1; May 35: 1; May 36: 1; May 37: 1; May 38: 1; May 39: 1
MB/C Readiness | [107 empty] | For MB/C 1st time we change our regular PT to another VW group supplier Pinacle & Palette . Due to which scheduled is delayed but time line of redinessis asper plan.cost saving approx: 222,400EUR
Cubing Readiness |  | SOLL1 | [105 empty] | Supplier : Pinacle Cost : 140,000EUR Schedule is delayed due to nomination of new supplier with good cost saving & also not affecting time line of readiness. CW 35 : Due to H7 head lamp issues. Modification need to be done on Cubing. Trasportation is delayed by one week.Eariler plan was CW37. CW 40: Recevied CW40/2.Installation is in Process KW40/6. CW41 :F & R bumper cubing trail was done. Some missing snaps & supports are observed on front cubing. CW 42:F & R cubing bumper trial was done. CW44: Readiness for internal presentaion in CW45. CW48: Internal presentaion & dry run done. CW49: Managment Presentation was done. | bar: May 21 to Sep 39; Oct 42 to Nov 47; Dec 53 to Jan 2; Jan 4 to Feb 5; Mar 12 to April 14; April 16 to April 17
SOLL2 | bar: May 21 to Nov 45; Nov 48; Feb 5 to Feb 6; Feb 8 to Mar 9; Mar 12; April 14 to April 15; May 18 to May 19; May 25 to May 26; May 30 to May 31; May 39 to May 40
IST | bar: May 21 to Nov 48; Feb 5 to Feb 6; Feb 8 to Mar 9; April 14 to April 15; April 17 to May 19; May 25 to May 26; May 30 to May 32; May 39 to May 40
Meisterbock Readiness
Meisterbock Readiness |  | SOLL1 | [105 empty] | Supplier : Palette Cost : 37600 Schedule is delayed due to nomination of new supplier with good cost saving & also not affecting time line of readiness. CW 35 : Fixtures ready delayed for Transportation CW 36: Fixtures ready delayed for Transportation CW 37 : Airfreight to India . CW 39: Received. CW 40: Meisterbock adapters Installation is in Process KW40/6. CW41 : MB/C prooving was done. CW44: Conflict observed for section F41_1. Task to Tech M to send CAD & Fugen plan comparison. Readiness for internal presentaion in CW45. CW48: Internal presentaion & dry run done. CW49: Managment Presentation was done. | bar: May 21 to Sep 39; Oct 42 to Nov 47; Dec 53 to Jan 2; Jan 4 to Feb 5; Mar 12 to April 14; April 16 to April 17
SOLL2 | bar: May 21 to Nov 45; Nov 48; Feb 5 to Feb 6; Feb 8 to Mar 9; Mar 12; April 14 to April 15; May 18 to May 19; May 25 to May 26; May 30 to May 31; May 39 to May 40
IST | bar: May 21 to Nov 49; Feb 8 to Mar 9; April 14 to April 15; April 17 to May 19; May 25 to May 26; May 30 to May 32; May 39 to May 40
Measurement fixtures Readiness
Measuring Fixture Readiness |  | SOLL1 | [105 empty] | Supplier : Palette Cost : 37600 Schedule is delayed due to nomination of new supplier with good cost saving & also not affecting time line of readiness. CW 35 : Fixtures ready delayed for Transportation CW 36: Fixtures ready delayed for Transportation CW 37 : Airfreight to India . CW 39 : Received. CW41 : Prooving was done. CW 42: Fender submitted for measurement. CW43: Fender Measurement is done. | bar: May 21 to Sep 39
SOLL2 | bar: May 21 to Nov 45; Nov 48; Feb 8 to Mar 9
IST | bar: May 21 to Nov 49; Feb 8 to Mar 9
Measurement Pro Readiness
Program Readiness |  | SOLL1 | [105 empty] | CW40: PMP received and In-house creation of Measurement Programme completed. FMK updates awaited from PMP Planning WOB KW40/5. CW 42:Fender measurement program is in check. CW44:Invoices awaited. CW11: Additional PMP point requested by SK MB PMP dept. on Fender ZSB. | bar: Jun 25 to Aug 36; Sep 38 to Nov 47
IST | bar: Jun 25 to Nov 47
SK251 PA Plant readiness
Boday Shop
Manufacturing of equipment , Buy parts |  | SOLL | [105 empty] | New Cell for Hood assembly, New fixture for Fender & Bracket assembly, Modification at matching line. | bar: Mar 12 to April 17
IST | bar: Mar 12 to April 14
Paint Shop
Paint shop readiness |  | SOLL | [105 empty] | Modification in Jigs. Change in Programming | bar: Feb 6 to Aug 33; Oct 42 to Oct 44; Mar 9 to Mar 13
IST | bar: Feb 6 to Aug 33; Oct 42 to Oct 44; Mar 9 to Mar 13
Assembly
New FEC , Head lamp & guide profile fixture
Assembly Readiness |  | SOLL | bar: Mar 12 to Nov 47
IST | bar: Mar 12 to Nov 47
Concept and Process design |  | SOLL
IST
Manufacturing and Bought outs |  | SOLL
IST
Installation |  | SOLL | bar: Nov 47
IST
Proveout |  | SOLL | bar: Nov 46
IST
Quality Project Tracking
Car Order for PVS & OS |  | SOLL | [105 empty] | 0S, 3 ASL cars ordering is done. 3 testing cars are pending. | bar: Aug 34; Oct 43
IST | bar: Aug 34; Oct 43
Stufen Plan | bar: Feb 5 to Feb 7
Parts status at each milestone | bar: Oct 43; Dec 50; Jan 1; Mar 9; Mar 13
Car Tracking PVS
Style : 1.5TDI 81KW DQ200 | 15876Km | SOLL | [105 empty] | Car Handover in CW11_6 | bar: Feb 6 to May 29
IST | bar: Mar 11 to April 17
Ambition : 1.5TDI 81KW MQ250 | 17276Km | SOLL | [105 empty] | Car Handover in CW12_5 | bar: Feb 5 to May 29
IST | bar: Mar 12 to April 17
Active : 1.6MPI 77KW MQ200 | 32802Km | SOLL | [105 empty] | ASL started from CW08/2 | bar: Feb 7 to May 29
IST | bar: Feb 7 to April 17
Style : 1.5TDI 81KW DQ200 |  | SOLL | bar: April 14; May 19
IST | bar: April 14
Car Tracking 0S
Style : 1.5TDI 81KW DQ200 |  | SOLL | bar: April 17 to May 29
IST
Active : 1.5TDI 81KW MQ250 |  | SOLL | bar: April 17 to May 29
IST
Ambition : 1.6MPI 77KW AQ250 |  | SOLL | bar: April 17 to May 29
IST
Style : 1.5TDI 81KW MQ250 | bar: May 30
Style : 1.6l MPI 77kW AQ250
Style : 1.5TDI 81KW MQ250
Ambition : 1.6MPI 77KW MQ200
MAF Drive Plan |  | SOLL | [105 empty] | CW44: Plant shut down is plan on CW18/16. Management drive plan must be check | bar: May 19; May 30
IST
Milestone release sign off from all dept
Body Shop Quality
CP5 |  |  | Oct 42: 1; Oct 43: 2; Oct 44: 2; Jan 2: 1; Jan 3: 1; Jan 4: 2; Feb 5: 5; Feb 6: 8; Feb 7: 10; Feb 8: 13; April 14: 1; April 15: 1; April 16: 2; April 17: 6; May 19: 11; May 20: 14; May 21: 17
[45 empty] | 3 | [13 empty] | 3 | 6 | 9 | 11 | 14 | [7 empty] | 3 | 7 |  | 12 | 15 | 18
[45 empty] | 2 | [13 empty] | 4 | 7 |  | 12 | [8 empty] | 4 | 8 |  | 13 | 16 | 19
[45 empty] | 3 | [25 empty] | 5 | 9
[45 empty] | 4 | [26 empty] | 10
Black body Audit | bar: Feb 7
TLD Audit
CP5 Audit |  |  | Oct 43: 1; Oct 44: 3 | CW43: CP5 audit was done for Sofa car. 1st Audit score was 3.2 & after rework 2.9
ZSB Bemustrung
Hangon parts/ Fitment Audit |  |  | Oct 41: 3 | CW41: Surface audit was done for Bonnet ZSB. Score is QK4.7.
Audit Software Update for skin pannel ( Resp IT)
Buy off's | [107 empty] | CW43: Sofa car buyoff is done | bar: Oct 43
Paint Shop Quality
CP5a |  | SOLL | Oct 44: 1; Nov 45: 2; Jan 4: 1; Feb 5: 3; Feb 6: 6; Feb 7: 8; Feb 8: 11; April 16: 1; April 17: 3; May 19: 8; May 20: 11; May 21: 12; May 22: 14; May 23: 17
[47 empty] | 3 | [11 empty] | 2 | 4 | 7 | 9 | 12 | [7 empty] | 2 | 4 |  | 9 |  | 13 | 15 | 18
[47 empty] | 4 | [12 empty] | 5 |  | 10 | 13 | [8 empty] | 5 |  | 10 |  |  | 16 | 19
[63 empty] | 14 | [8 empty] | 6
7
IST
KTL test
CP5a Audit |  |  | Oct 44: 1; Nov 45: 3
Corrosion test
Distructive test
Stone impact test
Hangon Parts TLD
Audit Software Update for skin pannel ( Resp IT)
Buy off's | bar: Oct 44
Assembly Shop Quality
CP8 |  | SOLL | Nov 47: 1; Feb 5: 1; Feb 6: 4; Feb 7: 7; Feb 8: 9; Mar 9: 12; April 17: 1; May 19: 4; May 20: 9; May 22: 12; May 23: 15; May 24: 18
[49 empty] | 2 | [10 empty] | 2 | 5 | 8 | 10 | 13 | [7 empty] | 2 |  | 5 | 10 |  | 13 | 16 | 19
[49 empty] | 3 | [10 empty] | 3 | 6 |  | 11 | 14 | [7 empty] | 3 |  | 6 | 11 |  | 14 | 17
[49 empty] | 4 | [24 empty] | 7
8
IST
Car buy off plan |  |  | Nov 48: 3; Nov 49: 1
Short drive plan
CP8 Audit |  |  | Nov 48: 3; Nov 49: 1; Feb 7: f
Launch planning
PDI
CP8 issues list
CP9 plan (Check list)
Audit Software Update for skin pannel ( Resp IT)
Batch release
Measurement Room
MB/C plan
ZSB release Plan
Measurement Fixture plan
FM catalogue
PMP plan
Problem Blatte
Lab
Color harmony
Evalauation plan
Capacity plan
Car Testing plan for PK5
Car Testing plan for FBW
Car Testing plan for SoSi
QAPP
Part Evaluation plan
EMPB status CP5 & CP7
Launch planning at supplier
QPN
QTR
Special firewall at supplier for presence activities
Launch plan at supplier
Fitment function plan Pilot hall |  | o
ASL & COP
Car Handover plan
Parts status at each milestone
Per week launch (Rs) planning
Special preparation
Special drives ( Region/ Hot/ Cold)
COP Plan
Vehicle Audit
Vehicle Audit Plan
Main issues in Vehicle Audit
Capacity
Rework & release plan
Safety
Vorderwagen release
Problem Blatte
Issues Tracking
Threats
Laser cut parts
SKD's
ASL Break down/ Accidents
KSK tracking
Asian Tooling
New supplier for Cubing
Safe launch plan
Safety Vorderwagen release
Body Audit points CP5
Paint Audit points CP5a
Assembly Audit Points CP8
ASL : Mileage completion status
COP : Emission release Powertrain wise
1.5 TDI DQ200 81 KW
1.5 TDI MQ250 81 KW
1.6 MPI AQ250 77KW
Management Drive issue
GQD Updates
Milestone release doc
Issue list weekly update
Bauprogram
CP5 |  | SOLL | Oct 42: 1; Oct 43: 2; Oct 44: 2; Jan 2: 1; Jan 3: 1; Jan 4: 2; Feb 5: 5; Feb 6: 8; Feb 7: 10; Feb 8: 13; April 14: 1; April 15: 1; April 16: 2; April 17: 6; May 19: 11; May 20: 14; May 21: 17
[45 empty] | 3 | [13 empty] | 3 | 6 | 9 | 11 | 14 | [7 empty] | 3 | 7 |  | 12 | 15 | 18
[45 empty] | 1 | [13 empty] | 4 | 7 |  | 12 | [8 empty] | 4 | 8 |  | 13 | 16 | 19
[45 empty] | 3 | [25 empty] | 5 | 9
[45 empty] | 4 | [26 empty] | 10
IST
CP5a |  | SOLL | Oct 44: 1; Nov 45: 2; Jan 4: 1; Feb 5: 3; Feb 6: 6; Feb 7: 8; Feb 8: 11; April 16: 1; April 17: 3; May 19: 8; May 20: 11; May 21: 12; May 22: 14; May 23: 17
[47 empty] | 3 | [11 empty] | 2 | 4 | 7 | 9 | 12 | [7 empty] | 2 | 4 |  | 9 |  | 13 | 15 | 18
[47 empty] | 4 | [12 empty] | 5 |  | 10 | 13 | [8 empty] | 5 |  | 10 |  |  | 16 | 19
[63 empty] | 14 | [8 empty] | 6
7
IST
CP8 |  | SOLL | Nov 47: 1; Feb 5: 1; Feb 6: 4; Feb 7: 7; Feb 8: 9; Mar 9: 12; April 17: 1; May 19: 4; May 20: 9; May 22: 12; May 23: 15; May 24: 18
[49 empty] | 2 | [10 empty] | 2 | 5 | 8 | 10 | 13 | [7 empty] | 2 |  | 5 | 10 |  | 13 | 16 | 19
[49 empty] | 3 | [10 empty] | 3 | 6 |  | 11 | 14 | [7 empty] | 3 |  | 6 | 11 |  | 14 | 17
[49 empty] | 4 | [24 empty] | 7
8
IST
BF
VFF
0 Series
PVS
Today
VFF Build start
0S release together with ICS
SOP release LAF drive test
Q Release
Cubing Manufacturing
Air Transport to India
Installation
Cubing ready for trail
Cubing Building
Management Dry run
Milestone Release Presentation
Meisterbock Manufacturing
Air Transport to India
Meisterbock ready for trail
Management Dry run
Milestone Release Presentation
Installation
Meisterbock Building
Measuring Fixture Mfg
Air Transport to India
Installation
Measuring Fixtures ready for trail
Program Readiness
Programing + QUIRL
Program Proving
Measurement of series parts & Fixture Proving
Mfg of equipment , Buy parts
Shipment
Installation
Optimization & Proving
Installation Start
RFQ,IAM,BM, PO
Paint & KTL Jigs Design and Mfg.
Readiness & Programming
Color Harmony & optimisation
Paint & KTL Jigs Design and Mfg.
Silk Blue Introduction SK251GP
RFQ,IAM,BM, PO
Concept and Process design
Manufacturing and Bought outs
Installation & Proveout
Concept and Process design start
Manufacturing and Bought outs
Installation Start
Bodies
R & D
Quality
Marketing Cars
B Release
Tool Construction
Sample from Tool Maker
Tool Transport
N3/N1/BMG Submission
N3 release
N1 release
BMG release
Plant Shutdown
Project Meilstons
International Visits
Domestic Visits
Lab Testing
Experts Visits
`
N1 Sub CW04/17
Car postponed to CW12
Car postponed to CW12
SOP Release
VFF Release
PVS Release

## Part Readiness
SK251 PA Project Time Plan
Description |  | 2015 | [52 empty] | 2016
|  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | April |  |  |  | May
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Current Timeline
Part Readiness
Fender(2) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | TO IN Laser cut | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | T3 Tool Release | 1 | 1 | N3* Sub | 1 | 1 | 1 | 2 N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release
IST | bar: Mar 11 to Aug 32
Bonnet outer(1) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | TO IN | T1 | 1 | T2 | 1 | T3 Tool Release | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release
IST | bar: Mar 11 to Aug 32
Bonnet Inner(1) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 TML | 1 | TO IN | T1 | 1 | T1 | 1 | 1 | T3 Tool Release | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | N1 Release
IST | bar: Mar 11 to Aug 32
Lock Reinforcement | SOLL | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: T0; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: N3* Sub; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 6: 1; Feb 7: 1; Feb 8: N1 Sub; Mar 9: 1; Mar 10: N1 Release
IST
Hinge Reinforcement (2) | SOLL | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: N3* Sub; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 6: 1; Feb 7: 1; Feb 8: N1 Sub; Mar 9: 1; Mar 10: N1 Release
IST
Fender Bracket (4) | SOLL | Mar 13: BF; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: N3* Sub; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: 1; Feb 6: 1; Feb 7: 1; Feb 8: N1 Sub; Mar 9: 1; Mar 10: N1 Release
IST
Front End Module | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | part for AMB | 1 | 1 | 1 | 1 | 1 | 1 | parts for VFF | Grain Goahead | 1 | 1 | 1 | Graining Completion | 1 | 1 | 1 | 1 | 1 | Grained parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Feb 9 to Aug 32
Front Bumper (5) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | Part for AMB | 1 | 1 | 1 | 1 | Parts for VFF | Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Grain Completion / Parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | BMG Sub. | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Mar 12 to Aug 32
Rear Bumper(10) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 IN | Part for AMB | 1 | 1 | 1 | 1 | Parts for VFF | Grain Go Ahead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Grain Completion / Parts for PVS | Tool Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | BMG Sub. | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Mar 12 to Aug 32
Tail lamp (2) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 T1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Buy off | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | BMG Sub. | 1 | 1 | 1 | N3 / BMG Release | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Apr 16 to Aug 32
Foam part (1) | SOLL | Mar 12: BF; Mar 13: 1; Mar 14: 1; Apr 15: 1; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: T0; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: 1; Nov 46: 1; Nov 47: 1; Nov 48: 1; Nov 49: 1; Dec 50: 1; Dec 51: 1; Dec 52: 1; Dec 53: 1; Jan 1: 1; Jan 2: 1; Jan 3: N3 Sub; Jan 4: 1; Feb 5: 1; Feb 6: N3 Release; Feb 7: 1; Feb 8: 1; Mar 9: 1; Mar 10: 1; Mar 11: 1; Mar 12: 1; Mar 13: 1; April 14: N1 Release
IST
Bumper Bar front (1) | SOLL | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | T0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Mar 11 to Aug 32
Decklid Chrom strip (1) | SOLL | [20 empty] | B Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1st parts for VFF | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| IST | May 21: B Release; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1
Hood Latch (1) | SOLL | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 MLF Release | 1 | BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release w/o BMG | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST
Air duct (2) | SOLL | Apr 15: BF; Apr 16: 1; Apr 17: 1; Apr 18: 1; May 19: 1; May 20: 1; May 21: 1; May 22: 1; Jun 23: 1; Jun 24: 1; Jun 25: 1; Jun 26: 1; Jun 27: 1; Jul 28: 1; Jul 29: 1; Jul 30: 1; Jul 31: 1; Aug 32: 1; Aug 33: 1; Aug 34: 1; Aug 35: 1; Aug 36: 1; Sep 37: 1; Sep 38: 1; Sep 39: 1; Sep 40: 1; Oct 41: 1; Oct 42: 1; Oct 43: 1; Oct 44: 1; Nov 45: N3 Sub; Nov 49: N3 Release; Jan 3: N1 Sub; Feb 5: N1 Release
IST
Bowden cable (1) | SOLL | [16 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | N3 Release | N1 Sub | 1 | 1 | 1 | 1 | 1 | 1 | BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1
IST
Horn (2) | SOLL | Apr 17: BF; May 21: BMG Sub.; Dec 53: N1 Sub; Jan 1: 1; Jan 2: 1; Jan 3: 1; Jan 4: N1 Release; Feb 5: 1; Feb 6: 1
IST
Radio (1) | SOLL | [7 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Parts for VFF | 1 | 1 | 1 | N3 Sub | 1 | 1 | 1 | 1 | 1 | 1 | N3 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N1 & BMG Sub. | 1 | 1 | 1 | 1 | 1 | 1 | BMG release | N1 Release | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
IST | bar: Jul 30 to Aug 33
Seat Covers (6) | SOLL | Nov 48: BF; Dec 51: N3 Sub; Dec 52: 1; Dec 53: N3 Release; Jan 1: 1; Jan 2: 1; Jan 3: BMG Sub.; Jan 4: Sub for Drive test; May 29: Drive test completion; May 30: BMG release; May 31: N1 Sub; May 32: 1; May 33: 1; May 34: 1; May 35: N1 Release; May 36: 1; May 37: 1
IST
Carrier Part (2) | SOLL | [8 empty] | BF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Sub | BMG Sub | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N3* Release | 1 | 1 | 1 | 1 | 1 | N1 Sub | 1 | 1 | 1 | N1 Release
IST
BF
VFF
0 Series
PVS
Today

## MBC
SK251 PA Project Time Plan
Description |  | 2015 | [52 empty] | 2016
|  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | April |  |  |  | May
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Current Timeline
Cubing Readiness
Cubing Manufacturing | SOLL | bar: Aug 33; Sep 37; Oct 42 to Nov 45; Nov 47; Dec 53 to Jan 2; Jan 4 to Feb 5; Mar 12 to April 14; April 16 to April 17
IST
Air Transport to India | SOLL
IST
Installation & comissioning @ VW India , by Launch support team | SOLL
IST
Cubing ready for Trials | SOLL
IST
Cubing Building | SOLL
IST
Management Dry run | SOLL
IST
Milestone Release Presentation | SOLL
IST
Meisterbock Readiness
Meisterbock Manufacturing | SOLL
IST
Air Transport to India | SOLL | bar: Aug 33
IST
Installation & comissioning @ VW India , by Launch support team | SOLL
IST
Meisterbock ready for Trials | SOLL | bar: Sep 37
IST
Meisterbock Building | SOLL | bar: Oct 42 to Oct 44; Dec 52 to Jan 1; Jan 4; Mar 12 to April 14
IST | bar: Jan 4
Management Dry run | SOLL | bar: Nov 45; Jan 3 to Jan 4; April 16
IST | bar: Jan 4
Milestone Release Presentation | SOLL | bar: Nov 47; Jan 4
IST
Measurement fixtures Readiness
Measuring Fixture Manufacturing | SOLL
IST
Air Transport to India | SOLL | bar: Aug 33
IST
Installation & comissioning @ VW India | SOLL
IST
Measuring Fixtures ready for Trials | SOLL | bar: Sep 37
IST
Details of Measurement Program Readiness
Receipt of PMP+FMK | SOLL
IST
Programming + QUIRL | SOLL
IST
Programme Proving | SOLL
IST
Measurement of series parts | SOLL | bar: Sep 39
IST
Fixture Proving | SOLL
IST
BF
VFF
0 Series
PVS
Today

## Lab Plan
SK251 PA Project Time Plan
Description |  | 2015 | [52 empty] | 2016
|  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | April |  |  |  | May
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Current Timeline
Lab Testing
Plastic Parts
SBBR | SOLL | bar: Nov 46 to Dec 50; Mar 11 to April 15; May 18 to May 22
IST | bar: Nov 46
Front Bumper | SOLL | bar: Sep 37 to Oct 43; Nov 46; Mar 12 to May 18; May 24 to May 30
IST | bar: Nov 46
Rear Bumper | SOLL | bar: Sep 37 to Oct 43; Nov 46; Mar 12 to May 18; May 24 to May 30
IST | bar: Nov 46
Trunk Lid Crome Strip | SOLL | bar: Nov 45 to Nov 49; Dec 51 to Jan 2; Mar 11 to April 15
IST | bar: Nov 46
Front End Carrier | SOLL | bar: Aug 35 to Oct 41; Nov 46; Mar 12 to May 18; May 22 to May 28
IST | bar: Nov 46
Foam Part | SOLL | bar: Jul 31 to Aug 35; Nov 46; Jan 3 to Feb 7; Mar 11 to April 15
IST | bar: Nov 46
Air Duct | SOLL | bar: Sep 37 to Oct 41; Nov 45 to Nov 49; Jan 3 to Feb 7
IST | bar: Nov 46
Instrument Cluster | SOLL | bar: Aug 36 to Sep 40; Oct 42 to Nov 46; Dec 50 to Jan 1
IST | bar: Nov 46
Metal Parts
Bonnet Inner | SOLL | bar: Sep 38 to Oct 43; Nov 46; Dec 50 to Jan 1; May 41 to May 45
IST | bar: Nov 46
Bonnet Outer | SOLL | bar: Sep 38 to Oct 43; Nov 46; Dec 50 to Jan 1; May 48 to May 52
IST | bar: Nov 46
Fender LH & RH | SOLL | bar: Nov 45 to Nov 49; Jan 1 to Feb 5; May 48 to May 52
IST | bar: Nov 46
Lock Reinforcement | SOLL | bar: Sep 38 to Oct 42; Nov 46; Nov 48 to Dec 52; Feb 8 to Mar 12
IST | bar: Nov 46
Hinge Reinforcement | SOLL | bar: Sep 38 to Oct 42; Nov 46; Nov 48 to Dec 52; Feb 8 to Mar 12
IST | bar: Nov 46
Fender Bracket | SOLL | bar: Sep 38 to Oct 42; Nov 46; Nov 48 to Dec 52; Feb 8 to Mar 12
IST | bar: Nov 46
Fender Bracket | SOLL | bar: Sep 38 to Oct 42; Nov 46; Nov 48 to Dec 52; Feb 8 to Mar 12
IST | bar: Nov 46
Hood latch | SOLL | bar: Sep 38 to May 22
IST | bar: Nov 46
Front Bumper Bar | SOLL | bar: Oct 42 to Dec 50; Jan 1 to Mar 9; April 16 to May 24
IST | bar: Nov 46
Carrier Part | SOLL | bar: Oct 42 to Nov 46; Dec 52 to Jan 3; April 16 to May 20
IST | bar: Nov 46
BF
VFF
0 Series
PVS
Today
4 Weeks
4 Weeks
4 Weeks
6 Weeks
6 Weeks
6 Weeks
6 Weeks
6 Weeks
6 Weeks
4 Weeks
4 Weeks
4 Weeks
6 Weeks
6 Weeks
6 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
4 Weeks
14 Weeks
14 Weeks
14 Weeks
8 Weeks
8 Weeks
8 Weeks
4 Weeks
4 Weeks
4 Weeks
6 Weeks

## Plant Readiness
SK251 PA Project Time Plan
Description |  | 2015 | [52 empty] | 2016
|  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | April |  |  |  | May
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Current Timeline
SK251 PA Plant readiness
Body Shop
Manufacturing of equipment , Buy parts | SOLL
IST
Shipment | SOLL
IST
Installation | SOLL
IST
Optimisation and Proving | SOLL
IST
Paint Shop
RFQ,IAM,BM, PO | SOLL
IST
Paint & KTL Jigs Design and Mfg. | SOLL
IST
Readiness and Programming & Profiling | SOLL
IST
Color Harmony & optimisation | SOLL | bar: Mar 9 to Mar 13
IST
Assembly
RFQ,IAM,BM, PO | SOLL
IST
Concept and Process design | SOLL
IST
Manufacturing and Bought outs | SOLL
IST
Installation | SOLL
IST
Proveout | SOLL
IST
BF
VFF
0 Series
PVS
Today
Readyness to Provide Existing colors SK251GP KW44
SK251GP
VFF Build start
Silk Blue Introduction SK251GP

## Budget Sheet
|  |  | 2015 | 2016
|  | Investment | 0.4 |  |  |  | I = Investment
|  | Launch Cost | 0.065 | 0.7 |  |  | L = Launch
Project | Category | BM | Description | Approved Value € | BM Value € | PO Value € | Remarks
SK251 PA | I |  | Front Cubing ( Bonnet, Fender & Front bumper cubing) | 131000
| I |  | Aussenmeisterbock ( Partial modification for front & rear end) | 15250
| I |  | Rear Cubing ( Rear Lamp & Rear Bumper Cubing) | 30000
| I |  | Measurement Fixture ( Bonnet & Fender) | 24500
| I |  | Programming, Debugging & evaluation | 10000
| I |  | Aeko Risk | 34500
| L |  | Commissioning & erection | 4750
| L |  | Tooling Expert ( Mr. Dirk Dauter) | 116000
|  |  | PMP & FMK | 34000

## Listen Learns
Listens learns : SK251 PA
Sr. No | Description | Area
1 | Head lamp: Two types of head lamp H4 & H7, but MBC manufactured with H4 only. | QMR
2 | Z support is missing for bumper | QMR
3 | Head lamp snaps are missing in Head lamp cubing. | QMR
4 | Cross bar fouling with KUM | QAPP/ R & D
5 | Bonnet Outer TMA data
6 | Tolerance Analysis with supplier ( Variable flushness conditions at various locations) | QMR/ QAPP
7 | Testing car planning ( SoSi/FBW Synergy)
8

## Good points
1 | Fugen plan
Advance communication of Car handover date to ASL team